## Features
Feature | Benefit(s)
Console Based Login | (1)Offers secure system login for Admin.Admin has Secure login and is able to access admin features
Console Based Registration | (1)Offers Admin to register Passengers(Potential Customers)
Console Based Customer Management | (1)Facility for Admin to efficiently manage Passenger data Including personal information, update customer details etc (2)Facility for Admin to efficiently update details or delete a passenger from their list.Admin also can view the entire passenger list.
UI Based Registration | (1)Offers secure system login for Passengers.Passengers has Secure login and is able to access features
UI Based Transaction processing | (2)Facility for Passengers to view deals on flight an also register complaints-UI

## Sprint1_productBacklog
S.No | Feature | Story Number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority | Sprint Number | Comments
1 | Menu Based Console Application – Programming | US001 | For an Administrator, you need to develop a menu list which represents the choices. | * An Administrator can able to perform the action based on the choices listed in the menu. * Option needs to be given to the Administrator. Program will end only by selecting the Exit option.  Passenger Registration (if Press 1): If administrator selects an option “1” then it prints the message on the console that “You have selected the Passenger Registration Feature.”  View Passenger Details (if Press 2): If administrator selects the option “2” then it prints the message on the console that “You have selected the View Passenger Details Feature.”  Search Passenger by PRN (if Press 3): If administrator selects the option “3” then it prints the message on the console that “You have selected the Search Passenger Feature.”option.  Update Passengers by Email Domain (if Press 4): If administrator selects an option “4” then it prints the message on the console that “You have selected the Update Passengers by Email Domain Feature.”  Delete Passengers by Mobile number (if Press 5): If administrator selects an option “5” then it prints the message on the console that “You have selected the Delete Passengers by Mobile number Feature.”  Exit (if press 6): If administrator selects the option “6” then system should print the message that “Good Bye Administrator!!. Terminating the Program”.  Invalid Option (other than 1 to 6): If Administrator is selecting the wrong option then system should print the message that “You have selected an inappropriate option. Kindly select an appropriate option.”. After that system will wail for an input from the administrator.
2 | Admin- Register(programming) | US002 | As Admin, I should be able to Register the Passengers .The below attributes are required to be handled by the application. FirstName-It should be of the Datatype String LastName-It should be of the Datatype String Password-It should be of the Datatype String Confirm Password-It should be of the Datatype String Email ID-It should be of the Datatype String Mobile Number-It should be of the Datatype Number Gender-It should be of the Datatype String City-It should be of the Datatype String | * Should be able to store data * Once Passenger is registered a unique PRN value must be generated for the passenger
3 | Admin- View(programming) | US003 | As Admin, I should be able to view all the Passengers registered | * Should be able to view all the active registered Passengers with all details including PRN * Should display only finite number of records per screen
4 | Admin- Search(programming) | US004 | As Admin, I should be able to search a Passengers registered using the PRN | * Should be able to view the Passengers details including PRN * Should display success or error messages
5 | Admin -Update(programming) | US005 | As Admin, I should be able to Update the details of the Passengers such as City and Name etc based on email | * Should be able to update details * Updates of Key Passenger info like PRN should not be permitted
6 | Admin - Delete(programming) | US006 | As admin, I should be able to delete the Passengers from the list of Passengers based on mobile number | * Should be able to delete pasengers * Success or error messages should be displayed
7 | Customer- Register(UI) | US007 | As a customer, I should be able to self register into the system .The below attributes are required to be handled by the application. UserName-Input should be of the type textBox. Data type is string FirstName-Input should of the TextBox Type.It should be of the Datatype String LastName-Input should of the TextBox Type.It should be of the Datatype String Password-Input should of the Password Type. Confirm Password-Input should of the Password Type. Email ID-Input should be of type email. Mobile Number-Input should of the TextBox Type.It should be of the Datatype Number Gender-Input should be Radio button. City-Input should dropdown. | * Should be able to enter the values on the screen * Once Passenger is registered the customer should able to login using the username and password registered * Success or Error response should be displayed on the screen with user friendly messages
8 | Customer Login(UI) | US008 | As a customer, I want to be able to login to the AirLine Portal and access the features of the website. I should be able to logout from the session. | * The log in page should be user id and password protected * The user ID can be alphabetic or alphanumeric and should have a minimum of 8 characters * Password should be minimum 10 characters including one special character, one upper case, one numeric.
9 | Customer- View Deals on Domestic and International Flights(UI) | US009 | As a customer, I should be able to view all the deals available on Domestic and International Flights available | * Should be able to view all the flights available with all details including Source and destination cities with costs,timings and date * Should display deals finite number of records per screen
10 | Customer- Register complaint(UI) | US010 | As a Customer, I want to be able to register complaint in the system. | * Should be able to register complaint regarding certain issues * Success or Error response should be displayed on the screen with user friendly messages