## Java
SlNo | Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority | Sprint Number
1 | Managing customers Registration page(Angular/NodeJs/ReactJS & Spring Boot,JDBC). | US001 | As a system user of online grocery management system, I should be able to register customer and redirect to the login after successful registering. | Registration : Customer and admin both should be able to register themselves to get access to login page.In order to connect with RestAPI you need to connect this page with back end, For that please refer 10_Sprint4_Backlog --> US008. Login : Customer and admin both should be able to login through the application from login page. To login, user will enter his 'username' and 'password' which will be queried from 2_PBL_SQL --> US_SQL_002. If customer tried to login through login page then he/she should be redirected to the home page. Validations & constraints : 1) Throughout the login process, ie. through the logout you need to maintain the session for the user. 2) If the user logs out of the website if they try to get to a specific page, they should be redirected back to the login page.display following columns (Product_id , Product_name, product) 3) You will be storing the registered user in the database for the application ie. Online grocery management system 4) The table for user will have columns, which can refernce from 2_PBL_SQL --> US_SQL_002, add one more column in the same with the user_role. By default if user is customer he will be marked as 'customer'. And if the admin registers him as an admin. 5) You need to ensure that all validations from 2_PBL_SQL ---> US_SQL_003 are performed and validated successfully. (Hint : Use @CrossOrigin annotation to enables cross-origin resource sharing only for this specific method.)
2 | Product Management to the website(Angular/NodeJs/ReactJS & Spring Boot,JDBC) | US002 | As a System Admin of online grocery Management System, I should be able to manage the product that customer can purchase. | As an admin for online grocery management system. I should able to insert and view the product from the application. Detailed Design description : 1) Insert Product : You will have to add "Add new product" link in the navigation bar of the web application. Once you click on the same you will be able to open "Add_product_form", from which you will be taking input for the product which can be referanced from 2_PBL_SQL --> US_SQL_003. Once the user enters all the information correctly pop-up should appear to say that "Product added successfully". All the text boxes should be reset. 2) View Product : You will have the "veiw product details" menu/link in the navigation bar of the wen application. Once you click on the same you will be able to navigate to the "View_Product_form", which fetches all the available records from the product table. Display following columns in the result (Product_id, Product_name, Product price, and so on please refer 2_PBL_SQL --> US_SQL_003). These will all be entered by the the admin. In each row add two buttons "Update" & "Delete". Validations & constraints : 1) While entering the information for the product name, product description should not be null or empty space. 2) You need to ensure that the price that you are trying to store should not exceed more that 10000. 3) You need to ensure that the session is managed from logging in the web application till the user logs out of the session. 4) You need to ensure that the data is stored & being fetched from database. In order to connect you product component with RestAPI please refer 10_Sprint4_Backlog --> US011
3 | Product Management to the website(Angular/NodeJs/ReactJS & Spring Boot,JDBC) | US003 | As a System Admin of online grocery Management System, I should be able to manage the product that customer can purchase. | As an admin for online grocery management system. I should able to update and delete the product from the application. Update Product : As a customer, Once i click on "update button" it should open "Update_product_form". For example, change the name of the product in the application. Delete Product : As a customer, i should be able to delete the record from the application. Validation and other constraints : 1) You need to ensure while updating the record you should be updating the records which correspond to that of the update button. Same is the case for deleting the record. 2) You should ensure that this web page is accessible to the user only when they are trying to log in with admin credentials. 3) Make sure that you are connecting this component to the RestAPI at backend, so that modification will reflect in the database. for that please refer 10_Sprint4_Backlog --> US012
4 | Changing password for customer(Angular/NodeJs/ReactJS & Spring Boot,JDBC) | US004 | As a customer, I should be able to change my password in online grocery management system application | As a customer, i should be able to change my password in online grocery management system application. Details design description : You will have to create a menu/Link to change the user password. Which will navigate to the "change_password" page, where usre can able to change there current password to new password. These form should have field such as, custmer_id, old_password, new_password and confirm password. Also create one button "Set Password". Once user enter correct information pop-up should show as "Your password changed successfully". Make sure that, new Password should be updated in the database, you need to connect login component with RestAPI at backend for that please refer 10_Sprint4_Backlog --> US009 Validation and constrainst : 1) You will have to store the user password into user table. 2) Make sure that, the password should have minumum 8 characters and maximum 13 characters. 3) Compare the input for New_password and confirm_password before saving into table. if they are not matching then show error message as "password fields are not mathcing !!!"
5 | View product catalog on online grocery management system.(Angular/NodeJs/ReactJS & Spring Boot,JDBC) | US005 | As a customer, I should be able to view products in the online grocery management system. | As a customer, I should be able to view products in the online grocery management system. Detailed design description : View Products : You will have to add "View_product" link/menu in navigation bar on the web application. Once user click on this link he should able to navigate to "View_Product page". On this page display a thumbnail image for the each product. Product details should be fetched from product table with all required details such as "Product_name, qty , product_price, product_Decription and so on". Validation and other constrainst : 1) Product details should be fetched from product table. 2) Handle database related exception during fetching data from databse.
6 | Implementing Coding standards(Angular/NodeJs/ReactJS & Spring Boot,JDBC) | US006 | Implementing appropriate Coding standards for online grocery application | Make sure the proper coding standard and MV* need to be implemented are followed. Details design description : 1) Make sure that proper coding stardards are been followed in each component. Provide comments wherever requies. 2) Follow proper naming convenction as per programming standards. 3) Implement MV* architecture for serperation concern. MV* helps developer to isolates the application logic from the user interface layer and supports separation of concerns. The view then uses the data prepared by the controller to generate a final presentable response.Mv* helps programmer to easily manage the components, also help to identify errors easily.
7 | Register and login user | US007 | User will be able to register and login in the applicaition | Register and login user: You need to make endpoint where you will be able to register user customer and log in the customer with the user name and password provided to it. Database that you will be using for the same: In this user story the database that we will use is from 2_PBL_SQL: US_SQL_002. You will need to add one more field in th table which states the role for the user which will be provided by the user. User story implimentation: You will be designing the rest api endpoint which you will be able to register the customer and Customer will also be able to login in the application. Please note both admin and customer will be using the same login endpoint in order for them to register in the application. - Register customer: In this end point you will be makeing an endpoint with which you will be able to register the user to the specific database table or the database table that has been refered to in the above mentioned table. Request: Post Request input: JSON data will be passed to the applicaiton Response: JSON data with the appropriate information status code: 201 - login for the customer: You will be designing the rest api endpoint whihc you will be able to login in the applciation. You will be using the same api endpoint and send the client or your front end which states what is the role for the user that is trying to login. Request: Post Request input: JSON data will be passed to the application, the data that you will passing is username and password for the user. Response: JSON data with the appropriate information along with the key called as a role which will have the value for the role of the user that is trying to login into the same. status code: 201
8 | Change Password | US008 | Change password for the user | Change password for the user: You will be making an endpoint for the user, from which user will be able to update his profile, which in turn will be able to update the password for that specific user. Database that you will be using for the same: In this user story the database that we will use is from 2_PBL_SQL: US_SQL_002. You will need to add one more field in th table which states the role for the user which will be provided by the user. User story implimentation: You will be designing the rest api endpoint which will help you update the information for the user specific. If the user doesnot provide with some information i.e. to update the password you will not be updating the password field (You will keep the password as it is). Request: PUT Request input: you will pass the customer id in the URL for the application, along with the json object, for the information that we need to update. Response: Response will be a json object with the appropriate information in the same, which states "user is updated successfully. status code: 201
9 | Search Product | US009 | View Product: Search product | View Product: Search product In this user story you will be able to retirve the record from the application. You can take the following example of url to get a better understanding for the retrival Senario 1: URL : http://localhost:8080/product You will be retriving all the inforamtion for product Senario 2: URL : http://localhost:8080/product?id=1 You will be retriving the inforamtion for product with the id = 1 Senario 3: URL : http://localhost:8080/product?name=sampleProduct You will be retriving the inforamtion for product with the name of the product entered Database that will be used in the application: In this user story the database that we will use is from 2_PBL_SQL: US_SQL_003. User story implimentation: You will be making a rest end point which will help you to retrive all the information based on the parameter that is given by the user. Request: GET Request input: you will be passing the values as a parameter in order to fetch the information as shown in the above senario Response: JSON array with the appropriate information status code: 200
10 | Insert and view product records | US010 | insert and view the record | insert and view the record User Story IDEA: you should be able to insert the record in the datbase and retrive the inserted record. Database that will be used in the application: In this user story the database that we will use is from 2_PBL_SQL: US_SQL_003. User story implimentation: You will be designing the rest api endpoint to insert and view record. Following are some of the inforamtion that you need to take care while developing the same - insert query. This is the end point with which you willl be able to enter the record in the database. Request: Post Request input: JSON data will be passed to the applicaiton Response: JSON data with the appropriate information status code: 201 If there is an error while developing the application, you application should return the approriate error message and error status - View query. This is the end point with which you willl be able to fetch the record in the database. Request: GET Request input: you will be passing nothing to it as you need to fetch all the record from the database Response: JSON array with the appropriate information status code: 200 If there is an error while developing the application, you application should return the approriate error message and error status
11 | Update and delete the product | US011 | update and delete the product | Update and delete the product User Story Idea You should be able to update the record and delete the record from the database. Database that will be used in the application: In this user story the database that we will use is from 2_PBL_SQL: US_SQL_003. User story implimentation You will be designing the rest api endpoint to update and delete record. Following are some of the inforamtion that you need to take care while developing the same. You will be needing to add a field in the applications, database which would be "discount" which is a int and by default it will be 0. - update record: This is the end point with which you will be able to update the product based on the product id. You need to store the update value from the user, if the user is not providing the discount values you will be updating it with the previous value that is already entered in the database. Request: PUT Request input: you will pass the prodcut id in the URL for the application, along with the json object, for the information that we need to update. Response: Response will be a json object with the appropriate information in the same. status code: 201 If there is an error while developing the application, you application should return the approriate error message and error status - delete record In this end point with which you will be able to delete the record in the database. Request: delete request input: you will be passing nothing but the id of the product in the url as this is all you will need to delete the product record from the database. Response: JSON array which shows the appriate message. status code: 200 If there is an error while developing the application, you application should return the approriate error message and error status
12 | Inserting documents in the batch(Using mongoDB) | US012 | As a admin, i should be able insert batch of documents(records) into the collection(table) dedicated for online grocery managament application. | As a system admin, i should be able insert batch of documents(records) into the collection(table) dedicated for online grocery managament application. Detailed Design description : 1) You have to Create product & customer collection using a suitable command. 2) Insert the ten documents into the product as well as customer collection respectively. You must use only one command to insert the 10 documents at once. After successful insertion, check weither the all data is inserted succesfully. (Hint : Use insertMany() method to perform above operation)
13 | Searching document from collection(Using MongoDB) | US013 | As a admin, i should be able to find/fetch any specific document from the existing collection in mongoDB database through web application. | As a system admin, i should be able to find/fetch any specific document from the existing collection in the MongoDB database through online grocery management system. Detailed Design description : 1) Use suitable command to check weither customer collection is present in the database. 2) Find the customer details which have the maximum total amount in the whishListed items. (Hint : Use find() method to perform above operation)
14 | Evaluating null fileds from collection(Using MongoDB) | US014 | As a admin, i should be able be evaluate input expression for null values from backend through suitable mongoDB aggregation function | As a admin, i should be able be evaluate input expression for null values from backend through suitable mongoDB aggregation function. Detailed Design description : 1)Using aggregation, find the number null fileds for input expression customer_address from customer collection. (Hint: Use $ifNull aggregate function to evaluate undefined values and missing fields as null)
15 | Code Integration | US015 | As a development team working on the online grocery ordering application, we want to ensure that all individual code components are integrated | As a development team working on the online grocery ordering application, we want to ensure that all individual code components are integrated and work on single DB. This integration will enable us to verify that the different parts of the system work together correctly. Acceptance Criteria: - Aim to integrate all individual modules, into fully functional online grocery ordering application. - Each module should interact with others, passing data effectively between them. - During the code integration, we expect data to flow correctly between modules without any errors. - The integrated code should preserve all functionalities and features implemented during the development of individual modules. And also maintain data consistency and integrity across the tables and all modules.
16 | Integration Testing | US016 | As a consumer, I want to use online grocery ordering application and interact with services | As a consumer, I want to use online grocery ordering application and interact with the producer's services seamlessly. Acceptance Criteria: - The Producer component should run the application and provide all the necessary functionalities. - The Consumer component should interact with producer's services through the User Interface (UI) and backend calls effectively.
17 | Functional Testing | US017 | As a developer, I want to perform functional testing | As a developer, I want to perform functional testing for all user stories to ensure application functionality. Acceptance Criteria: - Create test cases for each user story, covering both positive and negative scenarios. - Execute the test cases and verify that the application meets the expected behavior. - Ensure that appropriate exception handling is implemented in the application' to gracefully handle.
Note on E1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please specify which user story from backend need to be connected to Frontend for the application to work correctly.

## Python
SlNo | Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority | Sprint Number
1 | Customer Registration | US001 | As a customer, I want to register myself within the system using REST API endpoint. | As a new customer, I want to be able to register an account with Online Grocery Store by providing my details such as Name, Email, Contact Number, Address and etc. using a REST API endpoint. Acceptance Criteria: - The Registration Form should meet the system requirements. - The API should have a POST endpoint at '/api/register' that accepts JSON data with customer's details. - Email should be validated for correct format, throw an email format exception if the email is not in the correct format. - Upon successful registration, the customer's information should be store in the "customer" table in the database and corresponding entry with a unique email, userType(Customer), password and status (Default - Active / Inactive) should be created in the "login" table. - If the provided email is already registered, the API should return 409 conflict status and appropriate error message. - If successful, the API should return 201 Created Status and a success message. - If there is any issue with database connection during registration process, the API should respond with a 500 Internal Server Error status and an error message indicating that there was a server-side issue. - Handle any database related exception that may occur during the registration process.
2 | Administrator Registration | US002 | Register an Admin account programmatically from the backend using REST API endpoint. | Programmer should register an Admin account programmatically from the backend code and REST API, granting the account "active" status. Acceptance Criteria: - The application should expose a POST API endpint at 'api/admin/register' for Admin Registration. - The API should expect a JSON payload containing the following fields: 'Email' and 'Password'. - If the email format is invalid, the API should respond with a 400 Bad Request status and an error message that the email format is incorrect. - Upon successful registration, the API should create a new entry in the "login" table with provided 'email', 'password', 'userType' set to 'Admin' and 'status' set to 'Active'. The backend program should be able to add an administrator to the system by creating an entry in the "login" table with email(unique - not match with any customer's email), password, userType(Admin) and status (Active) - This administrator account should have exclusive access to perform all product-related operations. - If the admin registration is successful, the API should respond with a 201 Created status and a success message. - If there is any issue with database connection during registration process, the API should respond with a 500 Internal Server Error status and an error message indicating that there was a server-side issue. - Handle email format exception and any database related exception that may occur during the administrator registration process.
3 | User Login | US003 | As a registered customer or admin, I want to log in to my account using REST API | As a registered customer or admin, I want to log in to my account using my email(userName) and password using a REST API Acceptance Criteria: - The application should expose a POST API endpoint '/api/login' for user login. - The API should expect a JSON payload containing the following fields: 'email', 'password'. - If the password is matched, the user should be considered authenticated. - If the user's status is "Active", they should be granted access; otherwise, access should be denied. - If the user is "Admin", admin should have access to admin functionalities. - If the login is successful, the API should respond 200 OK status and a success message. - If the provided email or password does not match any registered user, the API should respond with a 401 Unauthorized status and an error message. - If the user status is "Deactivate", the API should respond with a 403 Forbidden status and an error message indicating that the account is deactivated. - If there is any issue with database connection during registration process, the API should respond with a 500 Internal Server Error status and an error message indicating that there was a server-side issue. - the API should respond with a 400 Bad Request status and an error message indicating that missing or invalid fields.
4 | Product Registration with Bulk Upload (Admin User Only) | US004 | As an Admin, I want to add new products by uploading CSV file using REST API | As an Admin user, I want to able to add new grocery products to the store either individually or by bulk uploading a CSV file containing product information. Acceptance Criteria: - The application should expose a POST API endpoint at '/api/admin/products/upload' for bulk product registration via CSV. - The API should validate the uploaded CSV file to ensure it contains the required columns and valid data. - If the CSV format is invalid, the API should respond with 400 Bad request status and an error message. - After completing the Bulk Upload, the API should respond with a 201 Created status and success message indicating the number of products successfully registered. - If there are any errors during CSV arsing or product registration, the API should respond with a 500 Internal Server Error and an error message. - If any mandatory columns/data are missing, the API should respond with 400 Bad Request and an error message.
5 | View Product Catalog | US005 | As a customer, I want to view the list of available grocery products using a REST API | As a customer, I want to view the list of available grocery products in the store. Acceptance Criteria: - The application should expose a GET API endpoint at 'api/products' for customers to view the product catalog. - When customer access the 'api/products' endpoint, thd API should retrieve a list of available products from the database. - The API response should be in JSON format, containing an array of product objects. - The API should return 200 OK status code upon successful retrieval of the product catalog. - If there are issues fetching the product data, the API should respond with a 500 Internal Server Error status and and error message.
6 | Add Products to Cart | US006 | As a customer, I want to add desired products | As a customer, I want to add desired products to the cart. Acceptance Criteria: - The application should expose a POST API endpoint at 'api/cart' for customers to add products in the cart. - When customer access the 'api/cart' endpoint, thd API should retrieve a list of products from the database that are added in the cart for the particular customer. - The API response should be in JSON format, containing an array of product objects. - The API should return 200 OK status code upon successful retrieval of the products in cart. - If there are issues fetching the cart's product data, the API should respond with a 500 Internal Server Error status and and error message.
7 | Update Cart Items | US007 | As a customer, I want to be able to change the quantity of items from my cart | As a customer I want to be able to update the quantity of items from my cart, we want to ensure that details are updated in the database as well. Acceptance Criteria: -The application should expose a PUT API endpoint 'api/update/<item_id>' for updating the quantity of items from the cart. -If the quantity is not valid, the API should respond with 400 status; Bad request and an error message. -If the user is in deactivated state and trying to update the quantity; the API should respond with 401 status; unauthorized access. -If quantity is updated sucessfully, the record should be updated as per the quantity and item_id provided by the user in the database. The API should respond with 200 status; updated successfully. -If there is any error while updating the quantity ,the API should respond with 500 status; internal server error and an error message indicating that there was a server-side issue.
8 | Place Order | US008 | As a customer, I want to place order for the items | As a customer, I want to place order for the items Acceptance Criteria: - The application should expose a POST API endpoint at 'api/orders' for customers to place order for the items. - When customer access the 'api/orders/place' endpoint, thd API should retrieve a list of products from which the customer can order. - The API response should be in JSON format, containing an array of order objects. - The API should return 200 OK status code upon successful retrieval of the products for an order. - If there are issues fetching the product data, the API should respond with a 500 Internal Server Error status and and error message. - If the customer is trying to order a product which does not exist, the API should respond with 404 status; product not found and an error message. - If the order is not having enough stock or get interrupted, the API should respond with 400 status; Bad request and an error message. - If the user is in deactivated state and trying to place an order; the API should respond with 401 status; unauthorized access.
9 | View Order History | US009 | As a customer, I want to view my order history | As a customer, I want to view my order history. Acceptance Criteria: - The application should expose a GET API endpoint at 'api/order_id' for customers to view the order history. - When customer access the 'api/products' endpoint, thd API should retrieve a list of all orders for a particular customer from the database (orders table). - The API response should be in JSON format, containing an array of order objects. - The API should return 200 OK status code upon successful retrieval of the order history. - If there are issues fetching the order history data, the API should respond with a 500 Internal Server Error status and and error message.
10 | Customer Details Update | US010 | As a customer, I want to be able to update my personal details | As a customer I want to be able to update my personal details, we want to ensure that details are updated in the database as well. Acceptance Criteria: - The API should ensure that the customer is authenticated and authorised to update their own details. - The application should expose a PUT API endpoint at '/api/update/<user_id>' for updating account. - This API will be expecting a JSON payload from the user containing the following fields: 'Email', 'password', 'address', 'contact'. - If the credentials entered by user is correct along with the proper payload, but user is in deactivated state; the API should respond with 401 status; unauthorized access - If the user is not allowed to perform the modification, then the API should respond with 403 Forbidden, to indicate that the user does not have permission to perform the requested action. - If any of the details are missing in the payload the API should respond with 400 status; Bad request and an error message. - If the authenticated user is in active state. The record should updated as per the payload provided by the user in the database. The API should respond with 200 status; updated successfully. - If there is any error while updating the records ,the API should respond with 500 status; internal server error and an error message indicating that there was a server-side issue.
11 | Soft Delete Customer Account | US011 | As a customer, I want the option to deactivate my account | As a customer, I want the option to deactivate my account Acceptance Criteria: - The application should expose a PUT API endpoint '/api/deactivate/<user_id>' for deactivating account. - This API will not be expecting any payload from the user, apart from the parameter pass by the user in URL. - If the credentials entered by user is incorrect , the API should respond with 401 Unauthorised status; and an error message. - If the ID entered by user is correct, but user is already deactivated the API should respond with 403 Forbidden status; Bad request and an error message. - If the ID entered by user is correct and user is not in deactive state. You need to update the status for user to be "Deactivate".The API should respond with 200 status and a success message.
12 | Restore Customer Account | US012 | As a customer, I want to be able to restore my account | As a customer I want to be able to restore my account Acceptance Criteria: -The application should expose a PUT API endpoint '/api/activate/<user_id>' for activating account. -This API will not be expecting any payload from the user, apart from the parameter pass by the user in the URL. - If the credentials entered by user is incorrect , the API should respond with 401 Unauthorised status; and an error message. -If the ID entered by user is correct, but user is already active the API should respond with 400 status; Bad request and an error message. -If the ID entered by user is correct and user is not in active state. You need to update the status for user to be "Active".The API should respond with 200 status and a success message.
13 | Code Integration | US013 | As a development team working on the online grocery ordering application, we want to ensure that all individual code components are integrated | As a development team working on the online grocery ordering application, we want to ensure that all individual code components are integrated using REST API implementedin Flask and work on single DB. This integration will enable us to verify that the different parts of the system work together correctly. Acceptance Criteria: - Aim to integrate all individual modules, into fully functional online grocery ordering application. - All modules should be integrated through REST APIs. - Each module should interact with others, passing data effectively between them. - During the code integration, we expect data to flow correctly between modules without any errors. - The integrated code should preserve all functionalities and features implemented during the development of individual modules. And also maintain data consistency and integrity across the tables and all modules.
14 | Integration Testing | US014 | As a consumer, I want to use online grocery ordering application and interact with services | As a consumer, I want to use online grocery ordering application and interact with the producer's services seamlessly. Acceptance Criteria: - The Producer component should run the application and provide all the necessary functionalities. - The Consumer component should interact with producer's services through the User Interface (UI) and backend calls effectively.
15 | Functional Testing | US015 | As a developer, I want to perform functional testing | As a developer, I want to perform functional testing for all user stories to ensure application functionality. Acceptance Criteria: - Each endpoint should be individually tested. - Test the API endpoint with valid inputs and scenarios to verify that they produce expected outcomes. - Test each API endpoint with invalid inputs and scenarios to ensure that appropriate error responses are generated. - Verify that the API endpints properly validate input data, rejecting invalid requests. - Test endpoints that retrieve data, such as product catelog, order history, to ensure accurate and complete data retrieval. - Test endpoints that modify data, such as updating details (Customers / Products), to ensure accurate data modification - Verify that authorized actions can only be performed by authenticated users. - Test scenarios that could lead to errors, such as attempting to place an order with insufficient stock, and verify that appropriate error responses are returned.