## Features
Feature | Benefit(s)
Website Registration-UI | Offers Bank Employee to register themselves for Secure login and access admin features
Website Login-UI | Offers secure system login for the bank employees
Customer Management-UI | Facility for bank employees to efficiently manage Customer data Including personal information, account Details , update customer details
Transaction processing-UI | Facility for bank employees to efficiently view transaction details, deductions and charges

## Sprint 1 Product Backlog
S/No | Feature | Story Number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority | Sprint Number | Comments
1 | Customer Registration – UI | US001 | As a Customer, I want to be able to self register into the system with my details. | *Customer can able to enter the following information in the screen; After Successful verification of the Customer over the input data, The unique identification number will be generated for each Customer 1. Customer SSN Id: A text value for SNN ID 2. First Name: A text value for Customer name(Maximum 50 characters) 3. Last Name: A text value for Customer name(Maximum 50 characters) 4. Email: A text field to capture the Email of an Customer. 5. Password: A text value for Password(Maximum 30 characters) 6. Confirm Password: A text value for Password(Maximum 30 characters) ( Data Entered in Password and Confirm Password Should be Same ) 7. Address: A text area to capture street, city details(Maximum 100 characters) 8. Contact Number:Text field. Maximum 10 characters. 9. Register: Submit button. * After clicking the 'Register' button, a registration acknowledgment screen need to be displayed with a success message. "Customer Registration successful." in green color. * Also display the following attributes in the Acknowledgment screen; Customer Id (Randomly generated), Customer Name and Email. * The registration process is static only, no need to integrate with database.
2 | Customer Login – UI | US002 | As a Customer, I want to be able to self Login into the system with my Credentials. | Customer SSN Id: Text field. Password : A text value for Password. Maximum 30 characters (Password provided while registration). Login: Submit button. After clicking the 'Login' button, a registra acknowledgment popup (MessageBox) should be displayed "Customer Registration successful." in green color. Also the Customer should be redirected to Home Page
3 | Customer Data Management -UI | US003 | As aCustomer, I want to be able to Enter my account details so that i can create new customer in the system | Enter the values for input fields (on Screen) : Customer SSN id , Customer Name, Account Number , IFSC code, Account balance , Adhaar card No. , Pan Card No , Date Of Birth , Gender, Marital Status , Email , Address , Contact Number popup should be diplayed Cutomer Registration Successfull.
|  | Us004 | As a Customer, I want to be able to withdraw amount from My account so that i can create new customer in the system | 1. Should be able to enter the withdrawal amount. 2.Should be displayed on the screen”Minimum balance should be 500”, if the reamining balance after withdraw money is less than 500 (Minimum amount that can be withdrawn is 1000 ) 3. Should be able to check balance once amount is withdrawn
|  | Us005 | As an customer,I can deposit money By taking reference of account number and able to see the updated amount | 1. Should be able to enter the deposit amount. 2. Should be able to view the details after updating amount
4 | Customer Login-Programming | US006 | As a bank admin,I want to have a menu with options to create an account, deposit money,etc. So that I can conveniently perform various banking operations. | In the bank management system, a user needs to interact with a menu that provides options to perform different banking operations. The menu should include the following options: a. Create Account b. deposit amount c. withdraw money d. balance checking
5 | Customer account Management-Programming | US007 | As an Customer, I want to be able to create account in the System | Developer needs to input the following information from the console using programming to Enter Customer Details: Customer SSN No: A 7 digit number for Customer Name: A string field for Customer name(Maximum 50 characters) Email: A string field to capture the Email. Address: A string field to capture street, city details(Maximum 100 characters) Contact Number:Text field. Maximum 10 characters. Addhar Number:Text field. Maximum 12 characters. Pan Number: String field. Maximum 10 characters Account number : String field. Maximum 20 characters Initial deposit amount: Digit numbers Once all fields are taken as input, Customer details need to be inserted in array/list/appropriate Collection. After successful account creation, acknowledgment message need to be displayed on the console as "Account is created successfully".
|  | US008 | As an customer,I can deposit money By taking reference of account number and able to see the updated amount | 1. Should be able to enter the deposit amount. 2. Should be able to view the details after updating amount
|  | US009 | As an customer,I can withdraws money By taking reference of account number and able to see the updated amount | 1. Should be able to enter the withdrawal amount. 2.Should be displayed on the screen”Minimum balance should be 500”, if amount balance is less than 250 3. Should be able to view the details after updating amount
|  | US010 | As an Customer I want to Check balance. | 1. Should be able to view the details after updating amount
6 | Customer Registration - DB | US011 | As a financial data analyst, i want to able to Capture Customer personal Data in the Database | Create an customer Table with following Attributes (Columns ) 1. Customer SSN ID: A Numeric value for Employee ID (Primary key) 2. First Name: A text value for customer name(Maximum 50 characters) 3. Last Name: A text value for customer name(Maximum 50 characters) 4. Email: A text field to capture the Email of an customer. 5. Date Of Birth : A Date value (YYYY-MM-DD) 6. Address: A text value to capture street, city details(Maximum 100 characters) 7. Contact Number: Numeric value Maximum 10 digits. After Successful Creation of Table insert minimum 10 Demo records
7 | Customer Details Management-DB | US012 | As a customer, I want to view my personal information | After Successful insertion of customer records, customer will be able to view his details
|  | US013 | As a customer, I want to update my personal information | After Successful insertion of customer records, Customer will be able to update his details
8 | Customer Data Management - Unix | US014 | As a Admin i want to search Customer Data by there Employee Id | Sample Data: AccountNo,CustomerName,DateofAccountCreation,AccountType,Balance 180607, Rahul Varma,12.12.22,Savings,30000 180608, Sita Raman,12.12.22,Joint,50000 190607, Sheetal Patil,20.07.22,Current,40000 190617, Pooja Patil,04.08.22,Salary,70000 200607, Rahul Sharma,20.08.22,SAVINGS,20000 210617, Pooja Srikari,20.08.22,SALARY,25000 210607, Pooja Rewa,20.08.22,joint,35000 210527, Dan Stewart,04.08.22,current,35000 280707, Sia R,21.09.23,Savings,30000 220888, Sonali G,1.05.23,Savings,15000 search for a customers having account no as 190607 if not found print message as "Cusomer Details not available or Customer do not exist "
|  | US015 | As a Admin i want to search Customer Data by Account Type | Display the customers having balance greater than or equal to 30000.
9 | Employee Data Management - PL/SQL | US016 | As a data administrator, i want to be able to access data and perform Operations on data | "Create an Employee Table with following Attributes (Columns ) 1. Employee ID: A Numeric value for Employee ID (Primary key) 2. First Name: A text value for Employee name(Maximum 50 characters) 3. Last Name: A text value for Employee name(Maximum 50 characters) 4. Email: A text field to capture the Email of an Employee. 5. Contact Number: Numeric value Maximum 10 digits. 6. Designation : A text field to capture the Designation of an Employee. (Clerk , Manager, Accountant ) 7. Salary : Numeric value Maximum 10 digits. After Successful Creation of Table insert minimum 10 Demo records" After Successful insertion of records financial data analyst, will add 10% of salary rs (Bonus )in each Employee salary whoose designation is clerk Display name,designation and new salary of the updated employees
|  | US017 | As a data administrator, i want to be able to access data and perform Operations on data | Display the Employess having salary greater than or equal to 50000 and add 2% of salary as commision in salary Display name,designation and new salary of the updated employees