## UI
SlNo | Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority | Sprint Number | Comments
1 | Passenger Registration & Login – UI | US001 | As a Customer/User , I want to be able to self register & login nto the system with my details. | * User can see Home page where he/she can find two buttons Register & Login, Now click on register. * User can able to enter the following information in the Registration screen;  User Name: A text value for User name(Maximum 50 characters)  Email: A text field to capture the Email.  Password: A text value for Password(Maximum 30 characters)  Address: A text area to capture street, city details(Maximum 100 characters)  Contact Number: Text field. Maximum 10 characters.  Register: Submit button. * After clicking the 'Register' button, a registration acknowledgment screen need to be displayed with a success message. "User Registration successful." in green color. * Also display the following attributes in the Acknowledgment screen: User Id (Randomly generated), User Name and Email. * The registration process is static only, no need to integrate with database. * After login to the system using the userId and password, You will be directed to Home Page where User can book any Services available by selecting;
2 | Home Page – UI | US002 | As a Customer/User, I want to use the services in the home page | * Home page consists of : AC & Appliances repair, House Cleaning, Vehicle repair service, Product pickup & drop service. * User can select on any one of the services; For example, AC & Appliances: user can select any sub services of AC&Application repair: 1. AC repair 2. TV repair 3. Fridge repair 4. Washing machine repair *As a user now iam selecting AC repair : following information need to be taken from user  Date/Slot: A Date component to enter the service date with slot timing.  Address: A text area to capture street, city details(Maximum 100 characters)  Vender selection: A drop down with following Vender names (Atleast 3 names)  Amount : Non editable amount needs to be displayed in the non editable box.  Confirm booking : Submit button. * After clicking the 'Confirm booking' button, a booking acknowledgment screen need to be displayed with a success message. "Service Booked successfully" in green color. * Also display the following attributes in the Acknowledgment screen: Service Id (Randomly generated), Vender Name and Date/Slot. * Similarly the user needs to do for all remaining services (House Cleaning, Vehicle repair service, Product pickup & drop service).  House Cleaning: 1. 1BHK 2. 2BHK 3. 3BHK 4. Bathroom cleaning  Vehicle repair service 1. 2-Wheeler repair 2. 3-wheeler repair  Product pickup & drop service 1. Furniture 2. Groceries 3. Vehicles After selection of the any service , then user required to provide details as explained above - after selection of AC Service. * The Booking process is static only, no need to integrate with database. |  |  |  | 1
3 | Service Booking List – UI | US003 | As a Customer/User, I want to be able to login to the system and view the services used as a table (history of user). | * This screen shows rows with columns; User/Customer_ID ¦ User_Name ¦ Service_ID ¦ Date ¦ Slot ¦ Type of Service ¦ Status * There should be a pagination option with Next> and <Prev links. The default row size of the listing is 5. * Display static data with 8 Service booking details for the user/customer that need to be span in two pages and navigate using the pagination links.