## Sql
SlNo | Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority | Sprint Number | Comments
1 | User Registration – DB | US001 | As a Developer I want to create database table(s) So that I can store User information . | * The table should contain option for capturing the following information; User Id, User Name, Age, Email, password, Address, Contact number. * Design the attribute with proper data type and primary key. * Create the table script as an .sql file. * Insert 5 User information to this table. Create the insert script for the same. Also save it as an .sql file.
2 | Master Data – DB | US002 | As a Developer I want to create database table(s) So that I can store master data information in tables. | * Create a table to setup the master data details for Service Booking Status and insert the values. * Create a table to setup the master data details for Type of service & sub-service and insert the master data to the same. * Create a table to setup the master data details for Amount and insert the values. * Save the table schema and insert script in an .sql file.
3 | Service Booking – DB | US003 | As a Developer I want to create database table(s) So that I can store Service Booking information | * The table should contain option for capturing the following information; Service Id, Date, Slot, Type of service, Address, Amount, Status. * Design the attribute with proper data type and primary key. * Add a relationship with the User Registration table. * Create the table script as an .sql file. * Insert 10 booking details to this table. Create the insert script for the same. Also save it as an .sql file.
4 | Service Booking List – DB | US004 | As a Developer I want to retrieve all the service booking detail currently available including the User information to attempt the service by technician. | * Write a SQL statement for retrieving the Service booking details and User details together in a query. * The query result should contain the following attributes; Service Id ¦ Date ¦ Slot ¦ Type of Service ¦ Address ¦ Amount ¦ Status ¦ User Name ¦ Email ¦ Phone No.
5 | Date/Slot wise details List – DB | US005 | As a user / Admin I want to fetch availed services details in sorted order of date & slot. | * Write a query to fecth all availed services details in sorted order of date & slot. Also save it as an .sql file.