## Sheet1
SlNo | Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority | Sprint Number
1 | Patient Registration - Service | US001 | As a data administrator, I want to register within the system (Register Patients) | I want to be able to register an account with Hospital Management System by providing details such as 1. Patient Id 2. Patient Name 3. Room Number 4. Doctor Id (doctor assigned to patient ) 5. Doctor Name 6. Age 7. Gender 8. Weight 9. Height 10. Blood Group 11. Address 12. Contact No Acceptance Criteria: - The Registration Form should meet the system requirements. - Upon successful registration, the patients information should be stored in the "Patients" table in the database. - Handle any database related exception that may occur during the registration process.
2 | Administrator Registration - Service | US002 | As a developer, I want to create webservice for registering an admin within the system (registerAdmin) | Programmer should register an Admin account programmatically from the backend. Acceptance Criteria: - The backend program should be able to add an administrator to the system by creating an entry in the "login" table with email(unique - not match with any Patient's email), password, userType(Admin) and status (Active) - This administrator account should have exclusive access to perform all product-related operations. - Handle email format exception and any database related exception that may occur during the administrator registration process.
3 | Admin Login - Service | US003 | As a developer, I want to create webservice for validating the userLogin (validateLogin) | As a registered admin, I want to log in to my account using my userName and password. Acceptance Criteria: - The login form should include fields for userName and password. - The application should validate the credentials properly by matching the password stored in the "login" table. - If the user account is deactivated, the application should not allow login for Patients. - Handle invalid credentials and database related exception that may occur during the login process.
4 | Patient Registration - Screen | US004 | As a developer, I want to create Patient Registration screen for registering the Patient, consume the webservice (registerPatient) | as a admin, i want to be able to register patient with 1. Patient Id 2. Patient Name 3. Room Number 4. Doctor Id (doctor assigned to patient ) 5. Doctor Name 6. Age 7. Gender 8. Weight 9. Height 10. Blood Group 11. Address 12. Contact No Acceptance Criteria: - The Registration Form should meet the system requirements. - Upon successful registration, the Patient's information should be stored in the "Patient" table in the database. - Handle any database related exception that may occur during the registration process.
5 | Administrator Registration - Screen | US005 | As a developer, I want to create Admin Registration screen for registering the Patient, consume the webservice (registerAdmin) | Programmer should register an Admin account programmatically from the backend. Acceptance Criteria: - The backend program should be able to add an administrator to the system by creating an entry in the "login" table with email(unique - not match with any Patient's email), password, userType(Admin) and status (Active) - This administrator account should have exclusive access to perform all product-related operations. - Handle email format exception and any database related exception that may occur during the administrator registration process.
6 | Admin Login - Screen | US006 | As a developer, I want to create Login screen for the application, consume the webservice (validateLogin) | As a registered admin, I want to log in to my account using my userName and password. Acceptance Criteria: - The login form should include fields for userName and password. - The application should validate the credentials properly by matching the password stored in the "login" table. - If the user account is deactivated, the application should not allow login for Patients. - Handle invalid credentials and database related exception that may occur during the login process.