## UI
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initiial Size Estimate (SP) | Business Priority | Sprint Number | Comments
Website Login | US001 | As a admission desk executive I want to be able to log in the hospital website with my user ID and password So that I carry out my transactions | * The log in page should be user id and password protected * The user ID can be alphabetic or alphanumeric and should have a minimum of 8 characters * Password should contain 10 characters including one special character, one upper case, one numeric. *Session Management should be done on Login and Logout.
Patient Details Management | US002 | As a admission desk executive I want to be able to capture new patient information So that I can create a new patient in the system | * Should be able to enter the values on the screen * Success or Error response should be displayed on the screen with user friendly messages
| US003 | As a admission desk executive I want to be able to edit existing patient information So that I can store the updated patient information in the system | * Should be able to view the details before updating * Updates of Key patient info like SSN should not be permitted * Success or Error response should be displayed on the screen with user friendly messages
| US004 | As a admission desk executive I want to be able to delete existing patient from system | * Should be able to view the details before deleting * Success or Error response should be displayed on the screen with user friendly messages
| US005 | As a admission desk executive I want to be able to view all the active patients currently admitted in the hospital | * Should be able to view all the active patients of the hospital * Should display only finite number of records per screen
Online Search | US006 | As a admission desk executive I want to be able to search for a patient So that I am able to view the details | * Should be able to search for the patient details using r patient Id * User friendly responses should be provided for both success & failure
Patient Billing | US007 | As a admission desk executive I want to be able to get existing patient information So that I can raise the bill for the patient | * Should be able to search for the patient details using patient Id * Should be able to calculate and print the room bill * Should be able to calcu;ate the pharmacy bill * Should be able to calculate the diagnostics bill * Should be able to calulate the total bill * User friendly responses should be provided for both success & failure Note