## Java
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initiial Size Estimate (SP) | Business Priority | Sprint Number | Comments
1 | Patient Details Managemnt-Programming | US001 | As a Admin desk executive,I want to have a menu with options to Add , Update , Delete , View Patient details So that I can keep track of patients. | In the Hospital management system, a Admin desk executive needs to interact with a menu that provides options to perform different data operations operations. The menu should include the following options: a. Add Patient Details b. Update Patient Details c. Delete Patient Details d. View Patient Details e. View Patient Details By Id
2 | Patient Details Management-Programming | US007 | As an Patient, I want to be able to create account in the System | Developer needs to input the following information from the console using programming to Enter Patient Details: 1. Patient Id 2. Patient Name 3. Room Number 4. Doctor Id (doctor assigned to patient ) 5. Doctor Name 6. Age 7. Gender 8. Weight 9. Height 10. Blood Group 11. Address 12. Contact No Once all fields are taken as input, Patient details need to be inserted in array/list/appropriate Collection. After successful account creation, acknowledgment message need to be displayed on the console as "Patient Details Entered successfully".
|  | US002 | As an Admin Desk Executive,I can update the patient details and able to view them | 1. Admin desk executive Should be able to update the patient details 2. Admin desk executive Should be able to view the patient details after updating .
|  | US003 | As an Admin desk executive , I can delete the patient details | Admin desk executive Should be able to delete the patient details
|  | US004 | As an Admin desk executive view all patient details | Admin desk executive should be able to view all patients details
3 | Search Patient Details - programming | US005 | As a admission desk executive I want to be able to search for a patient So that I am able to view the details | * Should be able to search for the patient details using r patient Id * User friendly responses should be provided for both success & failure