## User Stories
SlNo | Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority | Sprint Number
1 | Session Management Implementation | US_Sprint_Web_001 | Implementation of session management to protect all the pages except login and Registration Page | In this user story, you will be implementing the session management. You will be logging in the application with the help of the login page. You will maintain a session with the help of which you will be able to protect the route for the application. You will be protecting all the pages except for the login and registration page. As,user need to use login and registration in order to create an account and login into the same.
2 | View number of places visited as per the class (JDBC - fetch) | US_Sprint_Web_002 | As a user, I want to be able to view the number of places visited according to class | Add the following functionality to the UI made in 1_PBL_UI->US_UI_003 As an admin user for Train Ticket Booking System, I should be able to see a table with the data pertaining to the number of places visited according to class. -Admin should be able to access the page containing the table through a dedicated button or a Drop-down option button in the home page.(refer 1_PBL_UI->US_UI_003) -The page should contain the table having a title and having 4 columns i.e. Place, 1st Class, 2nd Class and 3rd Class and the rows containing the place name and number of visits respectively. -The page should also have a back button or a home button which allows the user to navigate back to the home page.
3 | View number of tickets booked per quarter (JDBC fetch) | US_Sprint_Web_003 | As a user, I want to be able to view the number of tickets booked per quarter | Add the following functionality to the UI made in 1_PBL_UI->US_UI_003 As an admin user for Train Ticket Booking System, I should be able to see a table with the data pertaining to the number of bookings per quarter. -Admin should be able to access the page containing the table through a dedicated button or a drop-down option button in the home page.(1_PBL_UI->US_UI_003) -The page should contain the table having a title and having 4 columns i.e. the 4 financial quarters and the rows should contain the number of bookings. -The page should also have a back button or a home button to navigate back to the home page. (Note:-Both view options can be added to the same page containing both table together or it could be in two separate pages)
4 | View all the booked tickets from the admin dashboard(JDBC-fetch) | US_Sprint_Web_004 | As an admin user, I should be able to see all the booked train tickets and the user who had booked it. | Add the following functionality to the UI made in 1_PBL_UI->US_UI_003 From the admin homepage, I should be able to navigate to a secondary page which displays a table having details of all the booked train tickets. -The page can be reached by a button/navlink on the admin homepage(refer: 1_PBL_UI->US_UI_003) -It should have a header/navbar with option to go back to the homepage -A table with title should be displayed on the page which displays the details of all the trains which are booked and the corresponding user who had made said booking.
5 | Show trains for given destination with seat availability(JSP-Servlet and JDBC) | US_Sprint_Web_005 | As a user, I want to be able to view and book train tickets | Add the following functionality to the UI made in 1_PBL_UI->US_UI_002 As a user, I should be able to search for trains to a specific destination and it should display trains to that destination having seat availability -A book train option should be displayed on the main user homepage which takes the user to the booking page(refer: 1_PBL_UI->US_UI_002) -The booking page should have form with boarding, destination, no of passengers -Once the data is submitted it needs to be checked against the train database and details of matching train should be displayed on the page. -The page should also have an option to book the ticket and have nav links/buttons to go back to the homepage
6 | View available trains(JSP-Servlet and JDBC fetch) | US_Sprint_Web_006 | As a user, I should be able to view all the available trains | Add the following functionality to the UI made in 1_PBL_UI->US_UI_002 As a user, I should be able to see all the available trains and the including the available seats on the train -The page should be reached through a redirect/link from the user homepage(refer: 1_PBL_UI->US_UI_002) -It should display the table containing the details all available trains -The user should be able to navigate back to the homepage
7 | Service layer implementation | US_Sprint_Web_007 | Implementation of service layer | You will be creating one more layer in the application to write the business logic for the application. Up to this point we have created Repository layer, Presentation layer and View part for the application. In case you have to add some business logic like encryption and other calculation, you will be writing the same in the service layer for the application.(Note: Functionalities starting from US_Sprint_Web_008 can be added to this layer)
8 | Password encryption | US_Sprint_Web_008 | Password encryption – simple Caesar cypher | Password encryption – simple Caesar cypher You will be encrypting the password field in the application with the help of Caesar Cypher. Information on Caesar Cypher: When we say Caesar cypher, we will be shifting the password value by some digit to the right. For example: Consider that we have alphabets as “ABCDEFGHIJKLMNOPQRSTUVWXYZ” if we try to shift it by 2 the updated alphabets would be “CDEFGHIJKLMNOPQRSTUVWXYZAB”. Hence if I have a string say “Dave” that would be stored as “Fcxg” Some caveats that you can make use of You can store number as it is no need to shift the number Special Character can be stored as it is no need to shift the same. You can decide by how many digits do you need to shift the alphabets. Design Document: User will not be aware of how many digits the password is being stored. That should be done in the service file automatically before storing in the database.
9 | Logout Option | US_Sprint_Web_009 | Create a logout option/button | In this user story you will be logging out of the application. Once the user is logged out you will be redirecting him to the login page. -Once the user is logged out of the session, they should not be able to access the protected route for the same. -If the user opens a tab, and tried to access the page. They should be redirected back the login page.
10 | Handling error pages | US_Sprint_Web_010 | Handling error pages | Handling error pages This functionality will be used for both: user and admin. If in case, there is an exception that is being occurred in your program you will be displaying the same in a custom page with proper error message: Example: For example, if while pasting a URL in the browser if the user is implementing the wrong URL. This should redirect the URL to the page that states: “The URL you have entered is not correct.”
11 | Code Integration | US_Sprint_Web_011 | As a development team working on the online train ticketing system, we want to ensure that all individual code components are integrated | As a development team working on the train ticketing system application, we want to ensure that all individual code components are integrated and work on single DB. This integration will enable us to verify that the different parts of the system work together correctly. Acceptance Criteria: - Aim to integrate all individual modules, into fully functional train ticketing system application. - Each module should interact with others, passing data effectively between them. - During the code integration, we expect data to flow correctly between modules without any errors. - The integrated code should preserve all functionalities and features implemented during the development of individual modules. And also maintain data consistency and integrity across the tables and all modules.
12 | Integration Testing and Integrating with spark database | US_Sprint_Web_012 | Integrate the application, so that it can have a smooth flow. | Integrate the application, so that it can have a smooth flow. Integration Testing: Like we discussed, you will be creating a lot of user stories and you need to make sure the flow for the same is also managed. And all the user stories are properly integrated with one another. Users don’t have the URL bar to navigate from one place to another. You need to test after each user stories the integration for the same is done in the proper manner. Once you are done with the integration testing for the application you need to start implementing it with a common database you can do the same with the help of sparks project that we will be providing you with.
13 | Functional Testing for the application need to be done: | US_Sprint_Web_013 | Functional Testing for the application | "Functional Testing for the application need to be done: You have a lot of user stories that you have created. Proper workflow is necessary for the same as well. While running the application you need to ensure functional testing and integration testing. Functional testing: Functional testing refers to the application’s function. The content of the user story is being implemented or not that needs to be determined. Once you have created the user story you need to test the story that you have implemented to see if it is in accordance with the requirement that has been assigned."
14 | Following the proper architecture for the application development | US_Sprint_Web_014 | Following the proper architecture for the application development | Following the proper architecture for the application development For this user story we want you to make sure that you are following the best practices for developing the web application. If you are making some common web pages that will be used across all webpages, you can structure it in such a way that you are able to find these web pages in the organized structure. Other things you can keep in mind are: You are following a proper MVC architecture for the same. You are separating the concern from the related entities. You are giving the proper variable name You are following the proper coding standard.

## Dashboard
SNo. | User Story | Description
1 | US_Sprint_Web_001 | Back-end
2 | US_Sprint_Web_002 | Front-end
3 | US_Sprint_Web_003 | Front-end
4 | US_Sprint_Web_004 | Front-end
5 | US_Sprint_Web_005 | Front-end
6 | US_Sprint_Web_006 | Front-end
7 | US_Sprint_Web_007 | Back-end
8 | US_Sprint_Web_008 | Back-end
9 | US_Sprint_Web_009 | Front-end
10 | US_Sprint_Web_010 | Back-End(Exception Handling)
11 | US_Sprint_Web_011 | Testing
12 | US_Sprint_Web_012 | Testing
13 | US_Sprint_Web_013 | Testing
14 | US_Sprint_Web_014 | Testing