## UI Backlog
SlNo | Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority | Sprint Number | Comments
1 | Log In - UI |  | As a customer I should be able to login to the application using the username and passwrod | Login page should have below details: -Username and Password: User ID:User ID: <textbox min 5 and max 20> Password: A text value for Password(Maximum 30 characters, Minimum one upper case, lower case and special character ) -Error message: Displaying appropriate specific error message for invalid input.. -Successful Login: User should redirected to a dashboard/Home page with role specifc options in it.
2 | Log In - UI |  | As a Officer I should be able to login to the application using the username and passwrod | Login page should have below details: -Username and Password: User ID:User ID: <textbox min 5 and max 20> Password: A text value for Password(Maximum 30 characters, Minimum one upper case, lower case and special character ) -Error message: Displaying appropriate specific error message for invalid input.. -Successful Login: User should redirected to a dashboard/Home page with role specifc options in it.
3 | Registration - UI |  | As a Customer, I want to be able to self register into the system with my details. | Consumer should be able to enter the following information in the screen; 1.Personal Information: - Customer Name: A text value for Customer name(Maximum 50 characters) - Email: A text field to capture the Email. - Mobile number: <select box and text box) - After choosing the country code, 10 digit mobile number should be entered in text box -Address: A text value for complete mailing Address, including ZIP code and parcel code 2.Username and Password: - User ID: <textbox min 5 and max 20> - Password: A text value for Password(Maximum 30 characters) - Confirm Password: A text value for confirm password(Maximum 30 characters) 3.Preferences: -Specify any preferences related to mail delivery, notifications, or other relevant options - Register: Submit button. - Reset : Reset button * After clicking the 'Register' button, a registration acknowledgment screen need to be displayed with a success message. "Consumer Registration successful." in green color. * Also display the following attributes in the Acknowledgment screen; Customer username(Randomly generated), Customer Name and Email.
4 | Homepage – UI |  | As a Customer, I want to view the Home Page of application with all required options relevant to customer. | * After login to the system using the customerId and password, customer can view the home page with following information in the screen; - At the right side, display Welcome <username>, - Top bar, have following menu 1)Home - onclicking it redirect to the same page . 2)Booking service- On clicking it should be able to proceed with the booking. 3)Tracking - On clicking it should be navigated to Tracking Screen 4)Previous Booking – On clicking it Should be navigated to Previous Booking Screen. 5) Contact Support- On clicking it Should be redirected to support page/ helper page 6) Logout – on clicking it should redirect to login page of the project, by clearing the userdetails from browser
5 | Homepage – UI |  | As an officer, I want to view the Home Page with options relevant to officer. | * After login to the system using the customerId and password, officer can view the home page with following information in the screen; - At the right side, display Welcome <username> - Top bar, have following menu 1)Home - onclicking it redirect to the same page . 2)Tracking - On clicking it should be navigated to Tracking Screen 3)Delivery Status - On clicking it should be redirected to Delivery Status Screen 4) Pickup Scheduling-On clicking it should be redirected to Pickup Scheduling Screen. 5) Previous Booking – On clicking it Should be navigated to Previous Booking Screen. 6) Logout – on clicking it should redirect to first page of the project
6 | Booking Service |  | As a Customer, I should to be able to book a service from Parcel Management System | Below details needs to be displayed when user clicks on Booking service in the home page : 1. Sender Information: (This need to pre-populate as read only based on the current user) -Name -Address -Contact details 2. Receiver Information/Customer information: -Name -Address -Pin Code -Contact details 3. Parcel Details: -Size and weight -Contents description (for tracking and safety) 4. Shipping Options: -Choose delivery speed (standard, express, etc.) -Select packaging preferences (Standard Packaging, Custom Packaging, Eco-friendly Packaging, Fragile Item handling) 5. Date and Time Selection: -Choose preferred pickup or drop-off time 6. Service Cost and Payment: -Display the cost based on the chosen options (Parcel Size, Shipping options) -Provide different payment methods 7.Additional Services: -Insurance options -Tracking services 8. Implement all possible validations with custom validation messages.
7 | Booking Service |  | As an officer, I should to be able to book the service from Parcel Management System | Below details needs to be displayed : 1. Sender Information: (This need to be enabled for the officer to enter the details) -Name -Address -Contact details 2. Receiver Information/Customer information: -Name -Address -Pin Code -Contact details 3. Parcel Details: -Size and weight -Contents description (for tracking and safety) 4. Shipping Options: -Choose delivery speed (standard, express, etc.) -Select packaging preferences (Standard Packaging, Custom Packaging, Eco-friendly Packaging, Fragile Item handling) 5. Date and Time Selection: -Choose preferred pickup or drop-off time 6. Service Cost and Payment: -Display the cost based on the chosen options (Parcel Size, Shipping options) -Provide different payment methods 7.Additional Services: -Insurance options -Tracking services 8. Implement all possible validations with custom validation messages.
8 | Pay Bill – UI |  | As a Customer, I should be able to pay the booking service bill from "Booking Service Page" | In the Payment page, customer can view the following information in the screen; - At the right side , Welcome <username>, Logout button<onclicking it should be logged out> - Payment page should display the below details a) Bill Amount (should not be editable by the customer) b) Mode of Payment – Debit/Credit - Pay Now button - On Clicking will proceed to screen for entering the card details - Back to Home - On Clicking , it should redirect to booking service page On clicking the Pay Now button, it should be redirected to Screen where Customer can provide his Credit Card details to pay the bill -Credit Card <text as title>:(Read only) -Card No <16 digits> -Card Holder Name -Expiry Date <MM/YY> -CVV < 3 digits> - Make Payment<button > - On clicking the Make Payment button, "Payment Successful" message along with Booking ID and redirect to invoice page - Use javascript for the necessary actions.
9 | Invoice Page |  | As a customer/officer, I should be able to view the invoice once the payment is successful | The invoice page need to contain the below detail read only with print option -Receiver Name -Receiver Address -Receiver Pin -Receiver Mobile -Parcel Weight(g) -Parcel Contents Description -Parcel Delivery Type -Parcel Packing Preference -Parcel Pickup Time -Parcel Dropoff Time -Parcel Service Cost -Parcel Payment Time
10 | Tracking status – Customer (UI) |  | As a Customer, I should be able to track the status of my parcel by providing the tracking numbers. | * Customer can able to enter the following information in the tracking screen; After successful shipping of the package customer should be able to view the tracking status of the package which he/she boooked by providing the following details.: - Booking ID- A 12 digit number that is randomly generated after booking a package(Unique code) - Search button- Once clicked the page should display the status of the package.
11 | Tracking status – Officer (UI) |  | As a Officer, I should be able to check the status of a customer's package. | * After login to the system using the userId and password of the Officer , he/she can view the page with following information in the screen; - List of all the shipped package sorted latest on the top - A search box where the Officer can provide the Customer ID and Booking Id of a particular Customer. - Search button - Once clicked the page should display the status of the package.
12 | Pickup Scheduling -Officer(UI) |  | As an Officer I should be able to schedule pick-up of packages from the sender. | * The following details should be displayed for the officer to schedule a pickup: Officer should have option to search with Booking ID based on the result officer should able to provide a date and time after consultation with Customer - Booking ID of a particular customer - Date and Time a save button should save the information to the system. with proper message and validation.
14 | Delivery Update |  | As an officer I want to update the delivery status of the particular item | Based on the different points, officer should able to update the status of the package by searching Booking ID - Picked up - In Transit - Delivered - Returned
15 | Customer Support – UI |  | As a Customer, I should be able to view the contact details of customer support | In the Customer Support page, customer can view the following information in the screen; - At the right side , Welcome <username>, Logout button<onclicking it should be logged out> - Customer can able to view the following details for query/complaints a) Contact number b) Mail id c) Address
16 | Booking History – UI |  | As a Customer, I should be able to view the booking details. | In the Customer Booking history page , customer can able to view the following information in the screen; - At the right side , Welcome <username>, Logout button<onclicking it should be logged out> - Customer can able to view the following details for his/her previous booking Customer ID ¦ Booking ID ¦ Booking Date ¦ Receiver Name ¦ Delivered address ¦ Amount ¦Status - previous and next option need to be available in the screen.
17 | Booking History – UI |  | As an Officer, I should be able to view the booking details based on the User ID and Date Range | In the Officer Booking history page , officer can able to view the following information in the screen; - At the right side , Welcome <username>, Logout button<onclicking it should be logged out> - officer can able to view the following details for previous booking based on the customer ID and Date Range Customer ID ¦ Booking ID ¦ Booking Date ¦ Receiver Name ¦ Delivered address ¦ Amount¦Status - previous and next option need to be available in the screen.

## DB Backlog
SlNo | Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority | Sprint Number | Comments
1 | Storing User Data(Master table) – SQL | US001 | As a developer, I want to create tables so that I can store user details. | * The table(tbl_UserProfile) should have columns for UserID, FullName, Email, MobileNumber, and Password. - User_ID - FullName - Rec_Address - Email (Unique) - MobileNumber - Password - Role * Set the UserID column as the primary key. * Create the table script as an .sql file. * Save it as a users.sql file.
2 | Register User - SQL | US002 | As a developer I should be able to add user and store user data to the table | Prepare a SQL query to add data to the User Table - User_ID (Auto generated) - FullName - Address - Email - MobileNumber - Password - Role * Insert 5 users' information to this table. Create the insert script for the same. Also save it as a users.sql file. * This should validate the constrains
3 | Log in User - SQL | US003 | As a developer I should be able to login based on the roles. | Prepare a SQL query which validate the user credentials from the corresponding user table and return a boolean flag with Role. Input * User Name * Password Output (if Exists) * Role * User Name * Password
4 | Storing Booking Data – SQL |  | As a developer I need to create a table to store the booking information | Prepare a SQL query to create table to store the booking information - Booking_ID - User_ID - Rec_Name - Rec_Address - Rec_Pin - Rec_Mobile - Par_Weight_Gram - Par_Contents_Description - Par_Delivery_Type - Par_Packing_Preference - Par_PickupTime - Par_DropoffTime - Par_ServiceCost - Par_PaymentTime - Par_Status
5 | Retrieve the user information |  | As a developer I should be able to view the necessary details of user based on userID | Prepare a SQL query to fetch the details based on the userID -Name -Address -Contact details
6 | Booking Service |  | As a developer I need to store the booking information to the corresponding table | Prepare a SQL query which inserts the booking details into the table. - User_ID - Rec_Name - Rec_Address - Rec_Pin - Rec_Mobile - Par_Weight_Gram - Par_Contents_Description - Par_Delivery_Type - Par_Packing_Preference - Par_PickupTime - Par_DropoffTime - Par_ServiceCost - Par_PaymentTime These information need to save to the DB and BookingID need to be auto generated.
7 | Invoice Details |  | As a developer I should be able to view the invoice for the booking done | Prepare an SQL query to fetch the information based on the booking ID -Booking ID -Receiver Name -Receiver Address -Receiver Pin -Receiver Mobile -Parcel Weight(g) -Parcel Contents Description -Parcel Delivery Type -Parcel Packing Preference -Parcel Pickup Time -Parcel Dropoff Time -Parcel Service Cost -Parcel Payment Time
8 | Tracking status – Customer/ Officer |  | As a developer I need to view the latest ten bookings done by the customer sorted in descending order of booking | Prepare an SQL query which result the ten latest booking by a particular user, below fields need to be resulted Booking ID ¦ FullName ¦ Address ¦ Rec_Name ¦ Rec_Address ¦ Date of Boooking ¦Par_Status
9 | Pickup/ Drop update - Officer |  | As an officer I should be able to search the booking details based on Booking ID | Prepare SQL query to retrieve the below details based on the Booking ID. Booking ID ¦ FullName ¦ Address ¦ Rec_Name ¦ Rec_Address ¦ Date of Boooking ¦Par_Status ¦Par_PickupTime ¦ Par_DropoffTime
10 | Pickup/ Drop update - Officer |  | As an officer I should be able to update the Pick and Drop Date time based on booking ID | Prepare SQL query to update the Pick and Drop time based on the Booking ID.
11 | View delivery details - Officer |  | As an officer I should be able to update the Delivery Status of the Parcel | Prepare SQL Query to retrieve the delivery status of the Parcel based on the Booking ID and display the below items Booking ID ¦ FullName ¦ Address ¦ Rec_Name ¦ Rec_Address ¦ Date of Boooking ¦Par_Status ¦
12 | Delivery Update |  | As an officer I should be able to update the Delivery Status of the Parcel | Prepare SQL Query to update the delivery status of the Parcel based on the Booking ID
13 | Booking History - Customer |  | As a Customer, I should be able to view the booking details of specific user | Prepare a SQL query to retrieve the below booking history information Customer ID ¦ Booking ID ¦ Booking Date ¦ Receiver Name ¦ Delivered address ¦ Amount ¦Status
14 | Booking History - Officer |  | As an officer I should be able to view the booking history of a particular user with in date range in descending order of the Booking Date | Prepare and SQL query to retrieve the below booking history information Customer ID ¦ Booking ID ¦ Booking Date ¦ Receiver Name ¦ Delivered address ¦ Amount ¦Status Based on the Customer ID and Date Range

## Programming Backlog
SlNo | Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority | Sprint Number | Comments
1 | Menu (Array/ArrayList) |  | As a developer I should be able to register/login to the application | Developer needs to input the following information from the console using programming. 1. User Registration -if option entered is 1, it should prompt with details for user registration(refer US 2) 2. Log in - if option entered is 2, it should prompt with details for login(refer US 3)
2 | User Registration (Array/Array List) |  | As a customer I need to register to the System | As a Customer I need to register to the system using the below inputs - Customer Name: A text value for Customer name(Maximum 50 characters) - Email: A text field to capture the Email. - Mobile number: <select box and text box) - After choosing the country code, 10 digit mobile number should be entered in text box -Address: A text value for complete mailing Address, including ZIP code and Parcel code - User ID: <textbox min 5 and max 20> - Password: A text value for Password(Maximum 30 characters) - Confirm Password: A text value for confirm password(Maximum 30 characters) -Specify any preferences related to mail delivery, notifications, or other relevant options
2 | Log In (Array/Array List) |  | As a customer I should be able to login to the application using username and password | Login console should have below details: -Username and Password: User ID:User ID: <text value min 5 and max 20> Password: A text value for Password(Maximum 30 characters, Minimum one upper case, lower case and special character ) -Error message: Displaying appropriate specific error message for invalid input.. -Successful Login: User should redirected to a dashboard/Home page with role specific options in it.
3 | View Customer Menu (Array/Array List) |  | As a customer I should be able to see the Menus corresponding to my Role | Once the user is logged in successfully, System should display the Menus defined for the particular Role as below 1. Home 2. Booking service- On clicking it should be able to proceed with the booking. 3. Tracking - On clicking it should be navigated to Tracking Screen 4. Previous Booking – On clicking it Should be navigated to Previous Booking Screen. 5. Contact Support- On clicking it Should be redirected to support page/ helper page 6. Logout – on clicking it should redirect to login page of the project, by clearing the use
4 | View Officer Menu - (Array/Array List) |  | As an Officer I need to see the Menus correspond to my Role | Once the user is logged in successfully, System should display the Menus defined for the particular Role as Below 1) Home - on clicking it redirect to the same page . 2) Tracking - On clicking it should be navigated to Tracking Screen 3) Delivery Status - On clicking it should be redirected to Delivery Status Screen 4) Pickup Scheduling-On clicking it should be redirected to Pickup Scheduling Screen. 5) Previous Booking – On clicking it Should be navigated to Previous Booking Screen. 6) Logout – on clicking it should redirect to first page of the project
5 | Booking a Service - Customer (Array/Array List) |  | As a Customer I should be able to book a service from the application | Once the user clicks for the option of booking service, System should display below information of current user as senders details. -Name -Address -Contact details And system should able to capture the below information from the user. - Rec_Name - Rec_Address - Rec_Pin - Rec_Mobile - Par_Weight_Gram - Par_Contents_Description - Par_Delivery_Type - Par_Packing_Preference - Par_PickupTime - Par_DropoffTime These fields need to be captured / calculated by the system - Par_ServiceCost (Need to calculate the amount based on the choices done by the user) - Par_PaymentTime (System date and time
6 | Booking a Service - Officer (Array/Array List) |  | As an Officer I should be able to book a service from the application | Once the user clicks for the option of booking service, system should able to capture the below information from the user. - Rec_Name - Rec_Address - Rec_Pin - Rec_Mobile - Rec_Name - Rec_Address - Rec_Pin - Rec_Mobile - Par_Weight_Gram - Par_Contents_Description - Par_Delivery_Type - Par_Packing_Preference - Par_PickupTime - Par_DropoffTime These fields need to be captured / calculated by the system - Par_ServiceCost (Need to calculate the amount based on the choices done by the user) - Par_PaymentTime (System date and time) with a proper validation/ status messages to user
7 | Generate Invoice (Array/Array List) |  | As a user I should be able to generate invoice for the booking based on booking ID | Once the Booking is done user / Officer should able to view the invoice based on the booking id and display the below details. to fetch the information based on the booking ID -Booking ID -Receiver Name -Receiver Address -Receiver Pin -Receiver Mobile -Parcel Weight(g) -Parcel Contents Description -Parcel Delivery Type -Parcel Packing Preference -Parcel Pickup Time -Parcel Dropoff Time -Parcel Service Cost -Parcel Payment Time
8 | Tracking Status- Customer (Array/Array List) |  | As a customer I want to track my package status based on booking ID | Once the user clicks for the option of Tracking Status, system should able to capture the Booking ID from the user and return result set specific to current user only . And display the below details Booking ID ¦ FullName ¦ Address ¦ Rec_Name ¦ Rec_Address ¦ Date of Booking ¦Par_Status
9 | Tracking Status- Officer (Array/Array List) |  | As an officer I want to track my package status based on booking ID | Once the officer clicks for the option of Tracking Status, system should be able to capture the Booking ID and display the below details Booking ID ¦ FullName ¦ Address ¦ Rec_Name ¦ Rec_Address ¦ Date of Booking ¦Par_Status with a proper validation/ status messages to user
10 | Pick up and Drop update (Array/Array List) |  | As an officer I should be able to update the Pickup and Drop time based on booking ID | Once the officer choose the option for update Pick up Schedule, officer should able to enter the Booking ID and corresponding data need to be displayed Booking ID ¦ FullName ¦ Address ¦ Rec_Name ¦ Rec_Address ¦ Date of Booking ¦Par_Status ¦Par_PickupTime ¦ Par_DropoffTime and officer should get an option to add new pickup and Drop time which need to be updated in the system
11 | Delivery Status update (Array/Array List) |  | As an officer I should be able to update the Delivery Status of the Parcel based on booking ID | Once the officer choose the option for Delivery Status update, Officer should able to enter the Booking ID and below details need to be displayed Booking ID ¦ FullName ¦ Address ¦ Rec_Name ¦ Rec_Address ¦ Date of Booking ¦Par_Status ¦ and officer need to update the Status to "Booked ¦In Transit ¦ Delivered ¦ Returned" with a proper validation/ status messages to user
12 | Booking History - Customer (Array/Array List) |  | As a Customer, I should be able to view the booking details of current user in descending order of booking | Once the officer choose for Previous Booking, Console should display the below details for the current user in the descending order of Booking Date Customer ID ¦ Booking ID ¦ Booking Date ¦ Receiver Name ¦ Delivered address ¦ Amount ¦Status
13 | Booking History - Officer (Array/Array List) |  | As an officer, I should be able to view the booking details based on the Date in descending order of booking date | Once the officer choose for Previous Booking Data based on the User ID and Range of Date, Console should display the below details for the current user in the descending order of Booking Date Customer ID ¦ Booking ID ¦ Booking Date ¦ Receiver Name ¦ Delivered address ¦ Amount ¦Status

## UNIX Backlog
SlNo | Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority | Sprint Number | Comments
1 | Delivered Parcel Count - Unix | US01 | As an admin, I want to retrieve the count of parcel records with status=Delivered | The file Parcel.txt contains following data in the order Customer ID ¦ Booking ID ¦ Booking Date ¦ Receiver Name ¦ Delivered address ¦ Amount ¦Status . The fields are separated by a pipe (“¦”). Write a Unix command to count the number of Delivereded parcels
2 | Booking Details– Unix | US02 | As an admin, I want to search for a particular booking so that I can view the booking details | You have a file having booking details. The file booking.txt file which contains data in the following order: Booking ID ¦ CustomerName ¦ Address ¦ Rec_Name ¦ Rec_Address ¦ Date of Booking ¦Par_Status Write a Unix command to display the details of BookingID: "XXXX" in the given order: BookingId¦ CustomerName ¦Par_Status If the given booking does not exist, then it should print "Booking details Not Found"
3 | Count of Parcel Bookings- Unix | US03 | As an admin, I want to find the total bookings done by a customer within a date range | You have a file with booking details of all consumers for the last 3 months in the given order. Booking ID ¦ CustomerName ¦ Address ¦ Rec_Name ¦ Rec_Address ¦ Date of Booking ¦Par_Status Write a unix command that find the total number of bookings done by a customer within a date range and prints the result in below format in descending order: Booking ID ¦ CustomerName ¦No of bookings
4 | Search Customer - Unix | US04 | As an admin, I want to search for a customer based on name that starts with "An" and display the corresponding records | The file customer.txt contains following data in the order Customer ID, Customer Name , Address, Email , Mobile The fields are separated by a comma (“,”). Write a Unix command to display the records where customer name starts with "An"
5 | Update Customer data - Unix | US05 | As an admin, I want to update the Email of a customer | The file customer.txt contains following data in the order Customer ID, Customer Name , Address, Email , Mobile The fields are separated by a comma (“,”). Write a Unix command to update the email of a customer.
6 | Extract Details– Unix | US06 | As an admin, I want to display the Booking ID, Customer Name and Date of Booking of a customer in descending order of booking ID | You have a file having booking details. The file booking.txt file which contains data in the following order: Booking ID ¦ CustomerName ¦ Address ¦ Rec_Name ¦ Rec_Address ¦ Date of Booking ¦Par_Status Write a Unix command to display the below details in descending order of booking id BookingId¦ CustomerName ¦Date of Booking